## Slide 1: Chapter 4: Project Integration Management
Information Technology Project Management, Seventh Edition

## Slide 2: Learning Objectives
Describe an overall framework for project integration management as it relates to the other project management knowledge areas and the project life cycle
Discuss the strategic planning process and apply different project selection methods. (Done in last weeks lecture business case, others the students can read
Explain the importance of creating a project charter to formally initiate projects. (already done in last weeks lecture)
Describe project management plan (already done in last week’s lecture.

## Slide 3: Learning Objectives
Explain project execution, its relationship to project planning, the factors related to successful results, and tools and techniques to assist in directing and managing project work
Describe the process of monitoring and controlling a project
Understand the integrated change control process, planning for and managing changes on information technology (IT) projects, and developing and using a change control system
Explain the importance of developing and following good procedures for closing phases/projects

## Slide 4: What is Project Integration Management
Coordinating the other project management knowledge areas (project management processes/tasks) throughout a projects life cycle.
Ensures that all elements of a project come together at the right times to complete a project successfully

## Slide 5: Project Integration Management Processes
1. Developing the project charter involves working with stakeholders to create the document that formally authorizes a project—the charter.
2. Developing the project management plan (creating a project proposal) involves coordinating all planning efforts to create a consistent, coherent document—the project management plan (various plans/documents- 9 knowledge Areas)
3. Directing and managing project work involves carrying out (executing) the project management plan by performing the activities included in it.

## Slide 6: Project Integration Management Processes (cont’d)
Monitoring and controlling project work involves overseeing activities to meet the performance objectives of the project
Performing integrated change (part of monitor/ control) control involves identifying, evaluating, and managing changes throughout the project life cycle.
Closing the project or phase involves finalizing all activities to formally close the project or phase.

## Slide 7: Why Project Integration Management (PIM)?
PIM is considered to be critical to overall project success
PIM enables project managers to:
  coordinate people, plans and work required to complete a project
  focus on the big picture of the project and steer the project team towards successful completion
  make swift decisions or empower someone in the team to make swift decisions (first time right decisions) when conflicts occur among project goals or people
  communicate key project information to top management
  effectively manage interface with stakeholders (provide stakeholder satisfaction)
    PM must establish and maintain good communication/relationship across organisation.
PIM must happen within the context of the entire organisation, not just within a project
  PM must integrate the work of project with ongoing operations of the organisation
PIM- is project management based on 9 knowledge areas
PIM is what gets performed in projects to deliver the projects successfully

## Slide 8: Strategic Planning and Project Selection
What project to pursue?
Should PMs be involved in decision making?
  Usually it is the top management responsibility
  Successful organisation know PMs can provide important information to help identify and select potential projects
  PMs, Product Managers or IT managers must take part in Strategic Planning

## Slide 9: Strategic Planning and Project Selection
Strategic planning involves determining long-term objectives, predicting future trends, and projecting the need for new products and services
Organizations often perform a SWOT analysis
  analyzing Strengths, Weaknesses, Opportunities, and Threats
As part of strategic planning, organizations
  identify potential projects
  use realistic methods to select which projects to work on
  formalize project initiation by issuing a project charter

## Slide 10: Methods for Selecting Projects
There are usually more projects than available time and resources to implement them
Methods for selecting projects include: (underlined bits- students can read from the text book)
focusing on broad organizational needs
categorizing information technology projects
performing net present value or other financial analyses (business case)
using a weighted scoring model (next lecture slide)
implementing a balanced scorecard

## Slide 11: 5. Weighted Scoring Model
A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria
    Identify criteria important to the project selection process
    Assign weights (percentages) to each criterion so they add up to 100%
    Assign scores (out of 100) to each criterion for each project
    Multiply the scores by the weights and get the total (add) weighted scores
The higher the weighted score, the better (get higher priority)

## Slide 12: Figure 4-7. Sample Weighted Scoring Model for Project Selection

## Slide 13: Developing a Project Management Plan
A project management plan is a document used to coordinate all project planning documents and help guide a project’s execution and control
Plans created in the other knowledge areas are critical part of project management plan
  i.e. plans and documents based on the other 9 knowledge areas are developed
    Project management plan (PMI knowledge area)

## Slide 14: Common Elements of a Project Management Plan
1. Introduction or overview of the project
  Project name, brief description of the project and the need it address (goals and reason for it), rough estimates (time & cost);
  names of project manager (contact for project information) & key team members;
  Deliverables of the project (project phase deliverables, software, hardware, technical report, training report)
  List of reference material (reference and summarize the plans produced for other knowledge areas)
  List of definitions (help to avoid confusion)
2. Description of how the project is organized
  Organisational charts (sponsor)
  Project responsibilities (identify project activities and people responsible for them)
  Document any major processes to follow on projects

## Slide 15: Common Elements of a Project Management Plan
3. Management and technical processes used on the project:
  Management objectives; management view, any major assumptions or constraint
  Project controls; how to monitor project progress (monthly or quarterly reviews); handle changes-what is the process for change control, level of management required to approve different types of changes.
  Risk/Issue management; how the team will identify, manage and control risks/issues
  Project staffing; number and types of people required on project
  Technical processes; describes specific methodologies a project might use

## Slide 16: Common Elements of a Project Management Plan
4. Work to be done,
  Major work packages – summarize the main work packages (Work Breakdown Structure - WBS) for the project and refer to appropriate sections of the scope management plan
  Other work related information – list hardware and software to be used on the project
  5. Schedule information
  Provide a summary overall project schedule (key deliverables and planned completion dates)
  Detailed schedule; provide more detailed information about project schedule. It should reference the schedule management plan and discuss dependencies among project activities that could affect project activities (network diagram, critical path)
  6. Budget information
  Summary budget
  Detailed budget

## Slide 17: Project Management Plan (PMP)
Produce various plans& documents (we will learn them through other 9 knowledge areas)
These plans & documents will be used to write (justify and support) the sections 1 to 6 shown in the template for PMP
Most sections of the PMP require providing summary based from the plans & documents, the actual plans & documentation must be provided in appendix of the PMP
PMP is the proposal for undertaking the project which needs approval from the management before you can embark on the actual project work
Next year for R & D project paper your team will be required to do PMP
  Present to get approval
  Do the necessary changes
  Then only your team will be allowed to carry out the project- work will be based on PMP

## Slide 18: Directing and Managing Project Work (Execution of PMP)
Involves managing and performing the work described in the project management plan
The majority of time and money is usually spent on execution
The application area of the project directly affects project execution because the products of the project are produced during execution

## Slide 19: Coordinating Planning and Execution
Project planning and execution are intertwined and inseparable activities
Those who will do the work should help to plan the work
Project managers must solicit input from the team to develop realistic plans

## Slide 20: Project Execution Tools and Techniques
Expert judgment: Experts can help project managers and their teams make many decisions related to project execution
Meetings: Meetings allow people to develop relationships, pick up on important body language or tone of voice, and have a dialogue to help resolve problems.

## Slide 21: Monitoring and Controlling Project Work (including change management)
Changes are inevitable on most projects, so it’s important to develop and follow a process to monitor and control changes (change management plan in PMP)
Monitoring project work includes collecting, measuring, and disseminating performance information
A baseline is the approved project management plan plus approved changes

## Slide 22: Performing Integrated Change Control
Three main objectives are:
  Influencing the factors that create changes to ensure that changes are beneficial
  Determining that a change has occurred
  Managing actual changes as they occur

## Slide 23: Change Control System
A change control system is a formal, documented process that describes when and how official project documents and work may be changed
Describes who is authorized to make changes and how to make them

## Slide 24: Closing Projects or Phases
To close a project or phase, you must finalize all activities and transfer the completed or cancelled work to the appropriate people
Main outputs include
  Final product, service, or result transition
  Organizational process asset updates

## Slide 25: Chapter Summary
Project integration management involves coordinating all of the other knowledge areas throughout a project’s life cycle
Main processes include
  Develop the project charter
  Develop the project management plan
  Direct and manage project execution
  Monitor and control project work
  Perform integrated change control
  Close the project or phase