## Slide 1: Chapter 7: Project Cost Management
Information Technology Project Management, Seventh Edition
Note: See the text itself for full citations.

## Slide 2: Learning Objectives
Understand the importance of project cost management
Explain basic project cost management principles, concepts, and terms
Describe the process of planning cost management
Discuss different types of cost estimates and methods for preparing them

## Slide 3: Learning Objectives
Understand the processes of determining a budget and preparing a cost estimate for an information technology (IT) project
Understand the benefits of earned value management

## Slide 4: What is Cost and Project Cost Management?
Cost is a resource sacrificed or foregone to achieve a specific objective or something given up in exchange
Costs are usually measured in monetary units like dollars
Project cost management includes the processes required to ensure that the project is completed within an approved budget

## Slide 5: Project Cost Management Processes
Planning cost management :determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost.
  Estimating costs: developing an approximation or estimate of the costs of the resources needed to complete a project
  Determining the budget: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
  Controlling costs: controlling changes to the project budget

## Slide 6: Basic Principles of Cost Management
Executive board better understand financial terms than IT terms , so IT project managers must speak their language
  Profits are revenues minus expenditures
  Profit margin is the ratio of revenues to profits
  Life cycle costing considers the total cost of ownership (TCO), or development plus support costs
  Cash flow analysis determines the estimated annual costs and benefits for a project and the resulting annual cash flow

## Slide 7: Types of Costs and Benefits
Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars
Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms
Direct costs are costs that can be directly related to producing the products and services of the project
Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project
Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs

## Slide 8: More Basic Principles of Cost Management
Learning curve theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced
Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
  Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
  Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns

## Slide 9: Planning Cost Management
The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
A cost management plan includes:
  Level of accuracy and units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 10: Estimating Costs
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
It’s important to know the types of cost estimates, how to prepare cost estimates, and typical problems associated with IT cost estimates

## Slide 11: Table 7-2. Types of Cost Estimates

## Slide 12: Cost Estimation Tools and Techniques
Basic tools and techniques for cost estimates:
  Analogous or top-down estimates: use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
  Bottom-up estimates: involve estimating individual work items or activities and summing them to get a project total
  Parametric modeling uses project characteristics (parameters) in a mathematical model to estimate project costs

## Slide 13: Typical Problems with IT Cost Estimates
Estimates are done too quickly
People lack estimating experience
Human beings are biased toward underestimation
Management desires accuracy

## Slide 14: Sample Cost Estimate
See pages 284-289 for a detailed example of creating a cost estimate for the Surveyor Pro project described in the opening case
Before creating an estimate, know what it will be used for, gather as much information as possible, and clarify the ground rules and assumptions for the estimate
If possible, estimate costs by major WBS categories
Create a cost model to make it easy to make changes to and document the estimate

## Slide 15: Figure 7-2. Surveyor Pro Project Cost Estimate

## Slide 16: Figure 7-3. Surveyor Pro Software Development Estimate

## Slide 17: Determining the Budget
Cost budgeting involves allocating the project cost estimate to individual work items over time
The WBS is a required input to the cost budgeting process since it defines the work items
Important goal is to produce a cost baseline
  a time-phased budget that project managers use to measure and monitor cost performance

## Slide 18: Figure 7-4. Surveyor Pro Project Cost Baseline

## Slide 19: Controlling Costs
Project cost control includes
  Monitoring cost performance
  Ensuring that only appropriate project changes are included in a revised cost baseline
  Informing project stakeholders of authorized changes to the project that will affect costs
Many organizations around the globe have problems with cost control

## Slide 20: Earned Value Management (EVM)
EVM is a project performance measurement technique that integrates scope, time, and cost data
Given a baseline (original plan plus approved changes), you can determine how well the project is meeting its goals
You must enter actual information periodically to use EVM
More and more organizations around the world are using EVM to help control project costs

## Slide 21: Earned Value Management Terms
The planned value (PV), also called the budget, is that portion of the approved total cost estimate planned to be spent on an activity during a given period
Actual cost (AC), called actual cost of work performed, is the total of direct and indirect costs incurred in accomplishing work on an activity during a given period
The earned value (EV), is an estimate of the value of the physical work actually completed
EV is based on the original planned costs for the project or activity and the rate at which the team is completing work on the project or activity to date

## Slide 22: EVM calculations
Rate of performance (RP) is the ratio of actual work completed to the percentage of work planned to have been completed at any given time during the life of the project or activity
Example
  A project involved purchasing and installing a new web server. According to the budget , it would take one week and will cost a total of $10,000 (labour cost, hardware and software).
    Planned Value (PV) = $10,000
  Suppose the server installation was halfway completed by the end of week 1.
    Rate of performance (RP) for first week = 50% (actual work completed)
    Earned value (EV) for first week = $5000 (earned value estimate after one week) 
    ($10,000 * 50%) [EV = PV * RP]
  It actually took two weeks and cost of $20,000 to purchase and install the new server. $15,000 of the cost was incurred in the first week and $5000 in the second week.
    Actual cost (AC) for first week = $15,000
    Cost variance (CV) for the first week = -$10,000  ($5000 - $15,000) [CV = EV – AC]
    If CV is negative means performing the work cost more than planned
    If CV is positive means performing the work cost less than planned

## Slide 23: EVM calculations
    Schedule Variance (SV) for the first week = -$5000  ($5000 - $10,000) [SV = EV – PV]
    If SV is negative means performing the work took longer than planned
    If SV is positive means performing the work took less than planned
    Cost performance index (CPI) for first week = 33%  (5000/15,000) * 100%  over the budget [CPI = (EV / AC) * 100]
    If CPI is equal to 1 or 100% means that cost incurred is what is in the budget
    If CPI is less than 1 or less than 100% means that the project is over the budget
    If CPI is greater than 1 or greater than 100% means that the project is under the budget
    Schedule performance index (SPI) for first week = 50%  ($5,000/ $10000) * 100%  behind the schedule ) [SPI = (EV / PV) * 100]
    If SPI is equal to 1 or 100% means that planned and actual cost are same on schedule)
    If SPI is less than 1 or less than 100% means that the project is behind the schedule
    If SPI is greater than 1 or greater than 100% means that the project is ahead of schedule

## Slide 24: Table 7-4. Earned Value Calculations for One Activity After Week One

## Slide 25: EVM calculations
Budget at Completion (BAC)
    Suppose for a project the total budget is $100,000 for 12 months.
    BAC for the project is $100,000
Estimate at Completion (EAC)
New estimated cost = $122, 308
For this project CPI is 81.76%
        EAC = (BAC/CPI) * 100
New estimated completion time = 13 months
For this project original time estimated was 12 months and SPI is 94.203
        Original time/ SPI * 100

## Slide 26: Table 7-5. Earned Value Formulas

## Slide 27: Rules of Thumb for Earned Value Numbers
Negative numbers for cost and schedule variance indicate problems in those areas
CPI and SPI less than 100% indicate problems
Problems mean the project is costing more than planned (over budget) or taking longer than planned (behind schedule)
The CPI can be used to calculate the estimate at completion (EAC)—an estimate of what it will cost to complete the project based on performance to date. The budget at completion (BAC) is the original total budget for the project

## Slide 28: Figure 7-5. Earned Value Chart for Project after Five Months

## Slide 29: Chapter Summary
Project cost management is a traditionally weak area of IT projects, and project managers must work to improve their ability to deliver projects within approved budgets
Main processes include
  Plan cost management
  Estimate costs
  Determine the budget
  Control costs